## Cover Sheet
Hackaton Neo4Aero
RACI Chart
Version 1.0
Data 11/26/2024

## Revision History
History
Version | Date | Modified By |  | Changes
1 | 2024-11-26 | Ivone Venancio |  | Document Created
Document Review and Sign-off
Name |  | Role |  | Action | Date Reviewed
Document References
Reference | Document |  | Link/Path

## RACI
Project Phase | Sub component | Description | Responsible (Who does the work) | Accountable (Approver) | Consulted (Opinions) | Informed (Advised of Progress) | Deadline
Business Partner | Training | Ministração do Workshop | Neo4j Partner (Eliezer Zarpelão) | Neo4j (Eliezer Zarpelão) and Avanade (Leandro Mariano) | Neo4j (Eliezer Zarpelão) and Avanade (Leandro Mariano) | Participantes | Primeiro dia ¦ 26/11/24
Business Partner | Training | Divisão das equipes do Hackton | Neo4j Partner (Eliezer Zarpelão) | Neo4j (Eliezer Zarpelão) and Avanade (Participantes) | Participantes | Participantes | Primeiro dia ¦ 26/11/24
Business Partner | Training | Definição dos pápeis | Neo4j (Eliezer Zarpelão) and Avanade (Participantes) | Neo4j (Eliezer Zarpelão) and Avanade (Leandro Mariano) | Participantes | Participantes | Primeiro dia ¦ 26/11/24
Project Management | Project Management | Criar sala de trabalho | Tech Lead (Leandro Mariano) | Tech Lead (Leandro Mariano) | Project Team (PM, Consultants) | Project Team (PM, Consultants) | Primeiro dia ¦ 26/11/24
Planning | Sollution Planning | Discussão técnica da solução | Technical Team (Tech Lead & Consultant) | Technical Team (Tech Lead & Consultant) | Equipe técnica (Tech Lead & Consultant) | Project Team (PM, TL, Consultants) | Primeiro dia ¦ 26/11/24
Planning | Requirements | Criar board Kanban no Miro | Project Manager (Ivone Venancio) | Technical Team (Tech Lead & Consultants) | Technical Team (Tech Lead & Consultants) | Project Team (PM, TL, Consultants) | Primeiro dia ¦ 26/11/24
Planning | Requirements | Levantamento dos requisitos | Project Team (PM, TL, Consultants) | Project Team (PM, TL, Consultants) | Project Team (PM, TL, Consultants) | Project Team (PM, TL, Consultants) | Primeiro dia ¦ 26/11/24
Planning | Build | Divisão de tarefas | Project Team (PM, TL, Consultants) | Project Team (PM, TL, Consultants) | Project Team (PM, TL, Consultants) | Project Team (PM, TL, Consultants) | Primeiro dia ¦ 26/11/24
Application | Build | Analisar a base de dados e preparar para uso | Tech Lead (Frederico Santos) | Technical Team (Tech Lead & Consultants) | Technical Team (Tech Lead & Consultants) | Project Team (PM, TL, Consultants) | Primeiro (26/11) & Segundo (27/11) dia
Application | Build | Complementar a base de dados com os dados relevantes | Tech Lead (Frederico Santos) | Technical Team (Tech Lead & Consultants) | Technical Team (Tech Lead & Consultants) | Project Team (PM, TL, Consultants) | Primeiro (26/11) & Segundo (27/11) dia
Application | Build | Analisar o método de upload da base no browser | Consultant (Vitor Brito) | Technical Team (Tech Lead & Consultants) | Technical Team (Tech Lead & Consultants) | Project Team (PM, TL, Consultants) | Primeiro (26/11) & Segundo (27/11) dia
Application | Build | Realizar upload da base de dados | Consultant (Vitor Brito) | Technical Team (Tech Lead & Consultants) | Technical Team (Tech Lead & Consultants) | Project Team (PM, TL, Consultants) | Segundo dia ¦ 27/11/24
Application | Build | Criar os nodes | Technical Team (Tech Lead & Consultant) | Technical Team (Tech Lead & Consultants) | Technical Team (Tech Lead & Consultants) | Project Team (PM, TL, Consultants) | Segundo dia ¦ 27/11/24
Application | Build | Criar os relacionamentos | Technical Team (Tech Lead & Consultant) | Technical Team (Tech Lead & Consultants) | Technical Team (Tech Lead & Consultants) | Project Team (PM, TL, Consultants) | Segundo dia ¦ 27/11/24
Application | Build | Construir as queries by Cypher | Technical Team (Tech Lead & Consultant) | Technical Team (Tech Lead & Consultants) | Technical Team (Tech Lead & Consultants) | Project Team (PM, TL, Consultants) | Segundo dia ¦ 27/11/24
Application | Build | Executar as queries | Technical Team (Tech Lead & Consultant) | Technical Team (Tech Lead & Consultants) | Technical Team (Tech Lead & Consultants) | Project Team (PM, TL, Consultants) | Segundo dia ¦ 27/11/24
Application | Build | Criar o repositório no GitHub | Tech Lead (Frederico Santos) | Technical Team (Tech Lead & Consultants) | Technical Team (Tech Lead & Consultants) | Project Team (PM, TL, Consultants) | Segundo dia ¦ 27/11/24
Application | Test | Validar as perguntas de negócios | Technical Team (Tech Lead & Consultant) | Technical Team (Tech Lead & Consultants) | Technical Team (Tech Lead & Consultants) | Project Team (PM, TL, Consultants) | Segundo dia ¦ 27/11/24
Application | Test | Registrar evidências das validações | Technical Team (Tech Lead & Consultant) | Technical Team (Tech Lead & Consultants) | Technical Team (Tech Lead & Consultants) | Project Team (PM, TL, Consultants) | Segundo dia ¦ 27/11/24
Application | Technical Architecture | Desenhar o modelo de dados | Consultant (Ramon Cairus) | Technical Team (Tech Lead & Consultants) | Technical Team (Tech Lead & Consultants) | Project Team (PM, TL, Consultants) | Primeiro (26/11) & Segundo (27/11) dia
Application | Technical Architecture | Desenhar a arquitetura de solução | Tech Lead (Frederico Santos) | Technical Team (Tech Lead & Consultants) | Technical Team (Tech Lead & Consultants) | Project Team (PM, TL, Consultants) | Primeiro (26/11) & Segundo (27/11) dia
Application | Analysis | Criar Dashboard (neodash) | Consultant (Vitor Brito) | Technical Team (Tech Lead & Consultants) | Technical Team (Tech Lead & Consultants) | Project Team (PM, TL, Consultants) | Primeiro (26/11) & Segundo (27/11) dia
Project Management | Release Management | Criar o repositório no GitHub | Tech Lead (Frederico Santos) | Technical Team (Tech Lead & Consultants) | Technical Team (Tech Lead & Consultants) | Project Team (PM, TL, Consultants) | Segundo dia ¦ 27/11/24
Project Management | Release Management | Deploy dos entregáveis (arquivos) no repositório | Tech Lead (Frederico Santos) | Tech Lead (Frederico Santos) | Project Manager (Ivone Venancio) | Neo4j Partner (Eliezer Zarpelão) | Segundo dia ¦ 27/11/24
Project Management | Project Management | Acompanhamento do planejamento do projeto | Project Manager (Ivone Venancio) | Tech Lead (Frederico Santos) | Consultants | Consultants | Primeiro (26/11) & Segundo (27/11) dia
Project Management | Project Management | Criar material da apresentação final do projeto | Project Manager (Ivone Venancio) | Tech Lead (Frederico Santos) | Consultants | Consultants | Primeiro (26/11) & Segundo (27/11) dia
Project Management | Project Management | Facilitar a apresentação final do projeto | Project Manager (Ivone Venancio) | Tech Lead (Frederico Santos) | Consultants | Neo4j Partner (Eliezer Zarpelão) | Segundo dia ¦ 27/11/24 a partir de 14h
Business Partner | Training | Oferecer feedback da applicação entregue | Neo4j Partner (Eliezer Zarpelão) | Neo4j Partner (Eliezer Zarpelão) | Neo4j Partner (Eliezer Zarpelão) | Project Team (PM, TL, Consultants) | Segundo dia ¦ 27/11/24 a partir de 14h